## GANTT Chart
GANTT CHART
| PROJECT TITLE |  | TopTechGamingSolutions.io |  |  |  |  | COMPANY NAME | [6 empty] | Top-Tech Gaming Solutions
| PROJECT MANAGER |  | Ashley Jean |  |  |  |  | DATE | [6 empty] | 2019-02-04
| POINT OF CONTACT: |  | Jennifer Jones
| WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(DAYS)
[8 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16
[8 empty] | Su | Mo | Tu | We | Tu | Fr | Sa | Su | Mo | Tu | We | Tu | Fr | Sa | Su | Mo | Tu | We | Tu | Fr | Sa | Su | Mo | Tu | We | Tu | Fr | Sa | Su | Mo | Tu | We | Tu | Fr | Sa | Su | Mo | Tu | We | Tu | Fr | Sa | Su | Mo | Tu | We | Tu | Fr | Sa | Su | Mo | Tu | We | Tu | Fr | Sa | Su | Mo | Tu | We | Tu | Fr | Sa | Su | Mo | Tu | We | Tu | Fr | Sa | Su | Mo | Tu | We | Tu | Fr | Sa | Su | Mo | Tu | We | Tu | Fr | Sa | Su | Mo | Tu | We | Tu | Fr | Sa | Su | Mo | Tu | We | Tu | Fr | Sa | Su | Mo | Tu | We | Tu | Fr | Sa | Su | Mo | Tu | We | Tu | Fr | Sa
| 1 | Project Requirements Analysis |  | 2019-02-04 | 2019-02-23 | 19 | 32%
| 1.1 | Project Analysis Meeting |  | 2019-02-04 | 2019-02-04 | 0 | 100% | bar: Week 1 Mo; Week 4 Mo to Week 4 Sa; Week 16 Su to Week 16 Mo
| 1.1.1 | Explore Software and Tools for Project |  | 2019-02-04 | 2019-02-23 | 19 | 32% | bar: Week 1 Mo to Week 3 Sa; Week 4 Mo to Week 4 Sa; Week 16 Su to Week 16 Mo
| 1.2 | Assign Tasks |  | 2019-02-11 | 2019-02-23 | 12 | 0% | bar: Week 2 Su to Week 3 Sa; Week 4 Mo to Week 4 Sa; Week 16 Su to Week 16 Mo
| 2 | Project Design |  | 2019-02-25 | 2019-03-11 | 16 | 0%
| 2.1 | Project Design Meeting |  | 2019-02-25 | 2019-02-25 | 0 | 0% | bar: Week 4 Mo to Week 4 Sa; Week 16 Su to Week 16 Mo
| 2.2 | Review Requirements |  | 2019-02-25 | 2019-02-25 | 3 | 0% | bar: Week 4 Mo to Week 4 Sa; Week 16 Su to Week 16 Mo
| 2.3 | Outline Design |  | 2019-02-26 | 2019-03-09 | 13 | 0% | bar: Week 4 Mo to Week 6 Sa; Week 16 Su to Week 16 Mo
| 2.4 | UI/UX Design |  | 2019-02-26 | 2019-03-04 | 8 | 0% | bar: Week 4 Mo to Week 5 Mo; Week 16 Su to Week 16 Mo
| 2.5 | Technical Status Presentation |  | 2019-03-11 | 2019-03-11 | 0 | 0% | bar: Week 4 Mo to Week 4 Sa; Week 16 Su to Week 16 Mo
| 3 | Implementation |  | 2019-03-11 | 2019-04-28 | 47 | 0%
| 3.1 | Project Implementation Meeting |  | 2019-03-10 | 2019-03-10 | 0 | 0% | bar: Week 4 Mo to Week 4 Sa; Week 16 Su to Week 16 Mo
| 3.2 | Validation Requirements |  | 2019-03-10 | 2019-03-10 | 0 | 0% | bar: Week 4 Mo to Week 4 Sa; Week 16 Su to Week 16 Mo
| 3.2.1 | Application Functionality Development |  | 2019-03-11 | 2019-04-28 | 47 | 0% | bar: Week 4 Mo to Week 4 Sa; Week 6 Su to Week 13 Su; Week 16 Su to Week 16 Mo
| 4 | Test |  | 2019-04-29 | 2019-05-12 | 13 | 0%
| 4.1 | Project Test Meeting |  | 2019-04-29 | 2019-04-29 | 0 | 0% | bar: Week 4 Mo to Week 4 Sa; Week 13 Mo; Week 16 Su to Week 16 Mo
| 4.2 | Performance System Test |  | 2019-04-29 | 2019-05-03 | 4 | 0% | bar: Week 4 Mo to Week 4 Sa; Week 13 Mo to Week 13 Fr; Week 16 Su to Week 16 Mo
| 4.3 | Document Issues Found |  | 2019-05-04 | 2019-05-05 | 1 | 0% | bar: Week 4 Mo to Week 4 Sa; Week 13 Sa to Week 14 Sa; Week 16 Su to Week 16 Mo
| 4.4 | Resolve Issuees Found |  | 2019-05-06 | 2019-05-12 | 6 | 0% | bar: Week 4 Mo to Week 4 Sa; Week 14 Su to Week 15 Su; Week 16 Su to Week 16 Mo
| 5 | Roll-Out |  | 2019-05-13 | 2019-05-20 | 7 | 0%
| 5.1 | Project Roll-Out Meeting |  | 2019-05-13 | 2019-05-19 | 0 | 0% | bar: Week 4 Mo to Week 4 Sa; Week 15 Mo to Week 16 Mo
| 5.2 | Presentation |  | 2019-05-20 | 2019-05-20 | 0 | 0% | bar: Week 4 Mo to Week 4 Sa; Week 16 Su to Week 16 Mo
*GANTT chart provided by Google templates
Formulas:
DURATION(DAYS) = DAYS([START DATE],[DUE DATE])